# Comprehensive Monitoring, Evaluation, Accountability and Learning (MEAL) Framework.

# School Feeding Programme – Enhancing Attendance, Nutrition, and Learning Outcomes

This document provides a comprehensive MEAL Framework for a School Feeding Programme. It outlines the programme logic, monitoring systems, evaluation approaches, accountability mechanisms, learning systems, reporting structures, indicators, responsibilities, and implementation plans.

## Programme Overview

| Component | Description |
| --- | --- |
| Programme Title | School Feeding Programme |
| Programme Duration | 10 Years |
| Implementation Area | Target underserved schools and communities |
| Target Beneficiaries | Primary school learners, pre-primary learners, school committees, cooks, teachers, and communities. |
| Programme Goal | To improve child nutrition, school attendance, retention, participation, and learning outcomes among vulnerable learners through sustainable and equitable school feeding interventions. |

### Programme Objectives

| Programme Objective | Objective Statement | Key Focus Areas | Expected Results |
| --- | --- | --- | --- |
| Objective 1: Improve School Attendance and Retention | Increase school attendance rates by at least 10% and improve learner retention across all programme schools by the end of Year 3. | - Reduce absenteeism among learners - Improve school participation and retention - Support vulnerable learners through regular meals - Promote consistent school attendance | - Increased learner attendance - Reduced dropout rates - Improved retention and transition rates - Increased learner participation in classroom activities |
| Objective 2: Improve Learner Nutrition and Wellbeing | Ensure at least 95% feeding coverage across programme schools and improve learner nutrition outcomes by Year 2. | - Provide nutritious daily meals - Improve dietary diversity among learners - Reduce short-term hunger - Promote safe food preparation and hygiene | - Increased feeding coverage - Improved learner health and energy levels - Reduced hunger-related absenteeism - Improved learner concentration and wellbeing |
| Objective 3: Strengthen Supply Chain and Food Management Systems | Improve food procurement, storage, stock management, and distribution systems to ensure uninterrupted meal provision. | - Improve food procurement systems - Strengthen school storage facilities - Enhance stock tracking and accountability - Reduce stock-outs and wastage | - Improved food availability in schools - Functional kitchens and storage systems - Reduced commodity losses - Timely food deliveries |
| Objective 4: Strengthen Accountability, Reporting, and MEAL Systems | Improve programme accountability, reporting compliance, data quality, and evidence-based decision-making. | - Improve school reporting compliance- Strengthen monitoring and supervision - Enhance data quality systems - Improve stakeholder accountability and transparency | - Timely and accurate reporting - Improved data quality and verification - Functional accountability mechanisms - Improved programme performance tracking |

## 2. Results Framework

| Level | Expected Results |
| --- | --- |
| Impact | Improved child nutrition, school attendance, retention, and learning outcomes across all programme schools. Long-term gains in literacy, numeracy, and reduced malnutrition prevalence. |
| Outcome 1 | Increased school attendance and retention: pupils consistently present, dropout rates reduced, and enrolment sustained across academic years. |
| Outcome 2 | Improved learner nutrition and wellbeing: pupils show better dietary diversity, reduced hunger, and improved health indicators (BMI-for-age, energy levels). |
| Outcome 3 | Strengthened accountability and reporting systems: timely, accurate data submitted by schools; improved transparency in resource use; enhanced stakeholder confidence. |
| Output 1 | Meals provided regularly: every enrolled child receives a nutritious meal daily, with ≥95% coverage across schools. |
| Output 2 | Supply chain and storage systems strengthened: schools equipped with functional kitchens, safe storage facilities, and efficient stock monitoring systems. |
| Output 3 | Stakeholders trained and monitoring operational systems: school committees, cooks, and MEAL staff trained in reporting, digital tools, and compliance standards. |
| Activity 1 | Procure and distribute food supplies: establish reliable procurement cycles, ensure timely deliveries, and maintain adequate stock levels at school kitchens. |
| Activity 2 | Conduct school feeding activities and monitor stock levels: daily preparation of meals, adherence to hygiene standards, and monthly audits of food stocks. |
| Activity 3 | Train stakeholders, collect data, and prepare reports: conduct regular training workshops, deploy digital reporting platforms, and produce monthly/quarterly dashboards. |

## 3. Key Activities

### Food Procurement and Distribution

Procurement of food commodities

Warehousing and stock management

Transportation to schools

Food distribution tracking

### Capacity Building

Training cooks on food safety

Training school committees

Training school focal persons on digital reporting tools

### Monitoring and Supervision

Routine school monitoring visits

Attendance verification

Stock verification

Data quality assessments

### Community Engagement

Parent sensitization meetings

Stakeholder forums

Nutrition awareness campaigns

## 4. Logical Framework (Logframe)

| Results Level | Indicators (SMART) | Means of Verification | Assumptions |
| --- | --- | --- | --- |
| Goal / Impact | Improved child nutrition, school attendance, retention, and learning outcomes. | - % reduction in malnutrition (stunting/wasting) - Literacy/numeracy scores ↑ 10% | - Donor funding and community contributions remain consistent throughout the programme. - Local government policies continue to allow and support NGO-led feeding initiatives. - No major external shocks (conflict, drought, pandemics) that disrupt school operations or food supply chains. - Communities value and support education and nutrition interventions. |
| Purpose / Outcomes | 1. Increased school attendance and retention. 2. Improved learner nutrition and wellbeing. 3. Strengthened accountability and reporting systems. | - Attendance ≥ 90% monthly - Dropout ↓ 20% annually - BMI-for-age scores improved - ≥95% of schools submit timely reports | 1. Parents and guardians encourage children to attend school regularly when meals are provided. 2. Meals are culturally acceptable, safe, and nutritionally balanced. 3. Schools cooperate with NGOs in implementing feeding and reporting systems. 4. NGO staff and volunteers remain motivated and available to deliver services. 5. Local food markets remain stable enough to support procurement. |
| Outputs | 1. Meals served regularly. 2. Supply chain and storage systems strengthened. 3. Stakeholders trained and monitoring systems operational. | - # of meals served per month - % of schools with functional kitchens/storage – # of stakeholders trained - % of schools using digital reporting tools | 1. Food deliveries from suppliers are timely and sufficient to meet demand. 2. Kitchens and storage facilities provided or supported by the NGO are maintained and functional. 3. Trained school committees and cooks remain active and engaged. 4. Digital or manual reporting tools provided by the NGO remain accessible and usable. 5. Community participation supports accountability and transparency. |
| Activities | 1. Procure and distribute food supplies. 2. Conduct school feeding activities and monitor stock levels. 3. Train stakeholders, collect data, and prepare reports. | - # of procurement cycles completed - # of feeding days per month - # of trainings conducted - % of schools submitting monthly reports | 1. Adequate donor funding is available for procurement and distribution cycles. 2. Procurement processes remain transparent and free from corruption. 3. Logistics systems (transport, warehousing) remain reliable and affordable for the NGO. 4. Continuous training and capacity building are supported by NGO management and partners. 5. Schools cooperate fully with monitoring, reporting, and training activities. |

## 5. Monitoring and Evaluation Framework

Project Title: School Feeding Programme – Enhancing Attendance and Nutrition

Goal: To improve child nutrition, school attendance, retention, and learning outcomes in underserved areas. Objectives:

- Increase school attendance rates by 10% by the end of Year 2.

- Ensure ≥95% feeding coverage across all programme schools.

- Strengthen accountability and reporting systems with ≥95% timely reporting compliance by Year 2.

| Indicator | Baseline | Target | Data Source | Data Collection Method | Responsible Person |
| --- | --- | --- | --- | --- | --- |
| % of pupils attending school daily | 85% (baseline) | ≥ 95% | School attendance registers EMIS | School registers checked, EMIS entries reviewed | School focal persons, QA/M&E Officers |
| Feeding coverage (% of enrolled pupils receiving meals) | 88% (baseline) | ≥ 95% | Feeding registers | Feeding reports compiled, SurveyCTO/RESCO forms submitted | School committees |
| % of schools submitting reports on time | 70% (baseline) | ≥ 95% every month | Monitoring dashboards, Salesforce, submission logs | Monitoring dashboards reviewed, submission logs tracked | QA/M&E Officers |
| % of schools with functional kitchens/storage | 60% (baseline) | ≥ 98% by Year 1 | Infrastructure audits, stock cards | Infrastructure audits conducted, stock cards verified | Logistics Team |
| % of reports passing DQA checks | 75% (baseline) | ≥ 95% every quarter | DQA tools, verification protocols | DQA tools applied, verification protocols followed | QA Team |
| # of stakeholders trained in reporting/accountability | 50% (baseline) | 97% every quarter | Training attendance logs | Training attendance logs recorded | Training Coordinators |
| Student retention rate | 88% (baseline) | ≥ 98% | Enrolment records, EMIS | Enrolment records reviewed, EMIS data analyzed | Education Program Officer |

### Data Sources

Nutrition surveys

EMIS reports

Salesforce database

SurveyCTO/Kobo/ODK submissions

Power BI dashboards

Monitoring reports

## 6. Indicator Reference Table

| Indicator | Definition | Formula | Frequency |
| --- | --- | --- | --- |
| Attendance Rate | % enrolled learners attending school | Attendance ÷ Enrolment × 100 | Monthly |
| Feeding Rate | % learners fed | Learners Fed ÷ Attendance × 100 | Monthly |
| Reporting Compliance | % schools reporting on time | Reports Submitted ÷ Expected Reports × 100 | Monthly |
| Stock Sufficiency | % schools with adequate stock | Schools with stock ÷ Total schools × 100 | Monthly |
| Dropout Rate | % learners leaving school | Dropouts ÷ Total enrolment × 100 | Quarterly |

## 7. Data Quality Assurance (DQA)

The programme will ensure data quality through routine verification, spot checks, audits, and database validation.

| DQA Activity | Frequency | Responsible |
| --- | --- | --- |
| Routine data verification | Monthly | QA Officers |
| Spot checks | Monthly | Field Officers |
| Data audits | Quarterly | MEAL Team |
| Database cleaning | Monthly | Data Team |
| School verification visits | Quarterly | Programme Officers |

### Common Data Quality Checks

Attendance exceeding enrolment

Feeding greater than attendance

Duplicate submissions

Missing reports

Inconsistent stock balances

Extreme variances

## 8. Evaluation Framework

| Evaluation Type | Purpose | Timing |
| --- | --- | --- |
| Baseline Assessment | Establish programme benchmarks | Programme start |
| Midline Evaluation | Assess implementation progress | Mid-programme |
| Endline Evaluation | Measure outcomes and impact | Programme end |
| Impact Evaluation | Assess long-term effects | End cycle |
| Thematic Review | Review specific programme areas | As needed |

## 9. Accountability Framework

| Mechanism | Purpose |
| --- | --- |
| Suggestion boxes | Anonymous beneficiary feedback |
| Hotline systems | Complaint and inquiry management |
| Community meetings | Stakeholder engagement |
| Monitoring visits | Direct beneficiary consultations |
| Digital forms | Online issue reporting |

### Complaint Handling Process

Receive complaint

Register and classify issue

Assign responsible officer

Investigate complaint

Resolve issues and communicate feedback

Close and document case

## 10. Learning Framework

| Learning Activity | Frequency |
| --- | --- |
| Reflection meetings | Monthly |
| Quarterly review workshops | Quarterly |
| Best practice documentation | Quarterly |
| Dashboard analysis sessions | Monthly |
| Annual learning forums | Annually |

## 11. Reporting Framework

| Report Type | Frequency | Audience | Responsibility |
| --- | --- | --- | --- |
| School feeding reports | Monthly | County teams | School focal persons |
| Dashboard performance reports | Monthly | Management | Data Team |
| QA reports | Monthly | Programme leadership | QA Team |
| Donor reports | Quarterly | Donors | Programme Manager |
| Evaluation reports | Annual | Stakeholders | MEAL Team |

## 12. Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Programme Manager | Overall programme oversight |
| MEAL Officer | Monitoring and reporting coordination |
| QA Officer | Data verification and quality assurance |
| Data Analyst | Dashboard development and analysis |
| Logistics Officer | Stock and supply monitoring |
| School Focal Persons | School-level reporting |
| Field Officers | Monitoring visits and supervision |
| School Committees | Community oversight |

## 13. Monitoring & Evaluation (M&E) Plan

| Activity | Monthly | Quarterly | Annual |
| --- | --- | --- | --- |
| School reporting | ✔ |  |  |
| Monitoring visits | ✔ |  |  |
| Data quality audits |  | ✔ |  |
| Outcome reviews |  | ✔ |  |
| Impact evaluations |  |  | ✔ |
| Stakeholder workshops |  | ✔ | ✔ |

## 14. Risk Management Framework

| Risk | Mitigation Strategy |
| --- | --- |
| Delayed food delivery | Buffer stock planning |
| Poor data quality | Routine DQAs and training |
| School non-reporting | Automated reminders |
| Funding delays | Contingency planning |
| High staff turnover | Continuous training |
| Commodity price inflation | Framework contracts |

## 15. Dashboard Recommendations

### Suggested KPIs

Total schools

Total enrolment

Total attendance

Attendance rate

Feeding rate

Meals served

Reporting compliance

Stock sufficiency

Schools stocked out

### Suggested Dashboard Pages

Executive Overview

Attendance Analysis

Feeding Performance

Stock Monitoring

Data Quality and QA

County Comparison

Trend Analysis

Volunteer Tracking